## About
Erewash Borough Council Performance Dashboard
Click on the links below to navigate the dashboard
Home | About this dashboard
Summary
Delivery Plan
Welcome to Erewash Borough Council's Performance Dashboard. The dashboard reports on four main areas: 1. 'Delivery Plan'. These are high level actions/projects for strategic and operational priorities across our services for the 2024-26 financial years. They also drive and measure progress against the Corporate Strategy. There are sub-tabs for each priority against the Corporate Strategy. 2. 'Performance Indicators'. A suite of key performance indicators that measure performance across the Council's services and underpin the Corporate Strategy. Again, these are split by Corporate Strategy priority. 3. 'Financial Summary'. A summary of the latest financial position 4. 'Risks'. A summary of the latest position against the risks on the Strategic Risk Register. Navigate through the dashboard using the links on the left hand side.
Performance Indicators
Financial Summary
Risks
Click the image below to see the 2024-28 Corporate Strategy

## Summary
Summary
Reporting period
This is the first reporting period for the new performance framework. Below is an overall summary for Corporate Strategy Actions and Key Performance Indicators. Updates and outturns for each by corporate priority are available on the relevant pages in this dashboard.
Q2 2024-25
Home
Summary | Corporate Strategy Actions
98% of Delivery Plan actions were on target or completed at the end of Quarter 2. There are no siginificant issues at this stage. For more information on the amber action and the two actions yet to start, see the individual Delivery Plan priorities.
Delivery Plan
Performance Indicators |  | Red | 0 | 0%
|  | Amber | 1 | 2.128%
Financial Summary |  | Green | 40 | 85.11%
|  | Completed | 6 | 12.77%
Risks
|  | Not started | 2
Key Performance Indicators
76% of all KPIs were on target at the end of Quarter 2, with another 19% within their tolerance level. There were 2 red indicators; for further information on these and all indicators, see the individual priority tabs.
|  | Red | 2 | 5.405%
|  | Amber | 7 | 18.92%
|  | Green | 28 | 75.68%
|  | Not started/annual | 6

## Delivery programme
Corporate Strategy Delivery Plan
Reporting period
Q2 2024-25 | We have developed a 4-year 'Delivery Plan' to both drive, and measure progress against our new Corporate Strategy. The actions within the plan have been split into Years 1 & 2 (2024/25 and 2025/26), and Years 3 & 4 (2026/27 and 2027/28). The plan is divided into the four priorities, and then by the objectives for each of those priorities: 1. Economy and Regeneration Promote regeneration Progress economic growth opportunities Improve housing supply 2. Supporting Communities Support residents with the cost of living Improve housing access and standards Improve quality of life 3. Sustainable Environment Deliver and respond to climate change Implement new waste management Look after the borough’s green spaces 4. A Modern Council Make best use of resources Ensure financial stability Utilise technology to transform service delivery Performance is reported quarterly, with a 'Red, Amber, Green' rating, to show whether the action is expected to be completed by its target date. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators
Financial Summary
Risks

## Priority 1
Economy and Regeneration Actions
Reporting period
Q2 2024-25
Summary All actions have commenced and are progressing to target, with the exception of 1.1a.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 1 | 9.091%
[5 empty] | Green | 10 | 90.91%
Summary |  |  |  |  | Completed | 0 | 0%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update
| Promote regeneration | 1.1a | Regeneration of Long Eaton High Street and creation of new managed workspace units at the Stable Block | Resources | Planning | Steve Birkinshaw | Amber | Long Eaton High St - Design ongoing through Derbyshire County Council partners. Construction expected to be completed Summer/Autumn 2026. Stable Block - Project delayed owing to defective works identified on site undertaken by previous contractor, additional costs implications still to be determined.
Financial Summary | Promote regeneration | 1.1b | Explore options for bringing empty commercial properties back into use in town centres | Resources | Planning | Steve Birkinshaw | Green | Enforcement action underway to issue Section 215 (untidy property) improvement notices. Dual purpose of improving public realm and prompting owners to bring them back into active economic use.
| Promote regeneration | 1.1c | Assessment of car park need and development of a Car Park Strategy | Environmental & Community Services | Operational Services | Steve Birkinshaw | Green | Assessment and draft Car Park Strategy completed. Next step is progress towards internal approval.
Risks | Progress economic growth opportunities | 1.2a | Review progress made in implementing Economic Development Strategy | Resources | Planning | Steve Birkinshaw | Green | Progress being made on all three strategic objectives. Strategic priority 1: Town Centres - 13 Empty Shop signage grants issued, to help bring vacant properties back into use. Strategic priorities 2: Rural Recreation - Rural Erewash Website and Marketing campaign launched. 150,000 people reached via social media and 17,000 visits to website. Strategic priority 3: Development and Business Growth - 10 Research and Development Grants issued, supporting 9 businesses.
| Progress economic growth opportunities | 1.2b | Continue to support the development of warehousing and industrial premises at the 200 acre New Stanton Park | Resources | Planning | Steve Birkinshaw | Green | Planning approval granted for 5 warehouse units on Plot 1 at New Stanton Park. Discussions underway with developers on potential further applications.
| Progress economic growth opportunities | 1.2c | Engage and survey local businesses to identify business needs and unlock barriers to growth through the EMCCA | Resources | Planning | Steve Birkinshaw | Green | Erewash Partnership undertaking a project which includes a survey of local business
| Progress economic growth opportunities | 1.2d | Promote entrepreneurial opportunities through SPF including research and development grants, retail signage and business grants | Resources | Planning | Steve Birkinshaw | Green | 13 Empty shops filled via signage grant (7 in Ilkeston, 6 in Long Eaton). 10 Research and Development Grants issued, supporting 9 businesses. £157,110 spent. Match funding from private sector- £82,092.
| Improve housing supply | 1.3a | Adopt Core Strategy subject to the results of the public examination and enable new housing development through the planning system | Resources | Planning | Steve Birkinshaw | Green | The Planning Inspector issued a post hearing letter on 4 September 2024 with a set of requirements. The council has responded to confirm how it will meet these requirements over a six month period. The inspector will then consider whether the plan is ready for adoption.
| Improve housing supply | 1.3b | Develop a new Housing Strategy/approach and action plan to meet local housing need | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Objectives drafted and action plan being developed in draft form for consideration at Homelessness and Supported Accommodation Board. Once agreed, there will be a period of internal and external consultation.
| Improve housing supply | 1.3c | Consider options for bringing empty residential properties back into use engaging with partners | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | A letter targeting owners of long-term empty homes has been drafted to gauge the level of involvement needed to tackle the 'low hanging fruit'. However, resources will need to be identified corporately to engage with landlords to make any significant impact on the many empty homes; this will be included in the draft housing strategy for consideration.
| Improve housing supply | 1.3d | With partners encourage and promote increasing the supply of affordable housing | Resources | Planning | Steve Birkinshaw | Green | Change in emphasis of Town Deal Galaxy Row Project will deliver affordable homes. Application underway to deliver affordable homes at the former Ilkeston Argos, funded by the EMCCA Brownfield housing fund. Currently preparing business case following success at Expression of Interest stage.

## Priority 2
Supporting Communities Actions
Reporting period
Q2 2024-25
Summary All commenced actions are on target, with one completed. Just one action not started yet, the new Council Tax support scheme. Due to various reasons, this is expected to carry through to the second half of the Corporate Strategy delivery plan.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 13 | 92.86%
Summary |  |  |  |  | Completed | 1 | 7.143%
Delivery Plan |  |  |  |  | Not started | 1
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update
| Support residents with the cost of living | 2.1a | Be an active member of the Financial Inclusion Network, deliver the cost of living action plan with partners and promote access to available support and services | Resources | Revenues and Benefits | Lisa Black | Green | Head of Revenues & Benefits is an active member of the regional financial inclusion group. We have also developed links with Citizens Advice Bureaux (CAB) to develop best practice in relation to debt collection and supporting households in cyclical debt. Led the development of the response to Household Support Fund 5 and established working relationships with Derbyshire County Council leads on HSF.
Financial Summary | Support residents with the cost of living | 2.1b | Implement new simplified and targeted Council Tax Support scheme for 2025/26 | Resources | Revenues and Benefits | Lisa Black | Not started | With the new Government suggesting changes to Council Tax (eg possible removal of Single Person discounts), coupled with the need to review other aspects of Council Tax premiums and discounts locally and the extension of the Household Support Fund, the scheme will be developed for implementation in 26/27.
| Support residents with the cost of living | 2.1c | Deliver Round 5 of the Household Support Fund (funded by Government) before September 2024 and review Discretionary Housing Policy to meet emerging and ongoing need | Resources | Revenues and Benefits | Lisa Black | Completed | Round 5 delivered. The council spent over £139,000 helping c. 140 households paying bills, helping people who are struggling with their rent and preventing people becoming homeless. EBC is now gearing up for HSF6 and is in direct liaison with DCC to ensure a timely response to any allocation for the period October 2024 to March 2025.
Risks | Support residents with the cost of living | 2.1d | Signpost and refer those in need to advice and support, including Armed Forced personnel and veterans | Resources | Revenues and Benefits | Lisa Black | Green | Quarterly liaison meetings with CAB are in place. Business case required to look at how EBC may fund direct debt advice so that direct referrals can be made for households experiencing financial vulnerability.
| Improve housing access and standards | 2.2a | Reinvigorate and refresh the Homelessness & Rough Sleeping Strategy for Erewash and respond to an increase in demand for homelessness services | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | This will be developed on the back of the service-led review of Housing Options, supported by Shelter, which is nearing completion and will help identify the objectives and establish the principal actions for the strategy. The developed draft will need internal and external consultation prior to CMT and Executive consideration.
| Improve housing access and standards | 2.2b | Establish an action plan for improving the quality of supported accommodation and reducing the growth in non-registered providers with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | The council's participation in the nationally funded Supported Housing Improvement Programme is well underway with actions identified through this and other work within the service running concurrently as overseen at the corporate Homelessness and Supported Accommodation Board. Draft action plan in place under the vision of the Board and being updated as needed.
| Improve housing access and standards | 2.2c | Take action to improve poor housing standards in the private rented sector | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Service restructure proposed to prepare the service to deliver the large government agenda in this arena. Areas include the impact of the Renters' Rights Bill, Supported Housing (Regulatory Oversight) Act 2023 and the Warm Homes: Local Grant funding offer for energy efficiency measures.
| Improve housing access and standards | 2.2d | Develop a Housing Assistance Policy under the Regulatory Reform Order to enable Disabled Facilities Grant funding to be used more flexibly | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Early draft developed which will need to be reviewed once we have determined the financial impact of DCC's proposal to end the Disability Design Team by 31/03/25; the delivery mechanism for Disabled Facilities Grants (DFGs). There will be a cost to EBC which will come out of this budget, affecting what the policy can achieve.
| Improve housing access and standards | 2.2e | Develop a longer-term strategy to increase the availability of temporary accommodation with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Additional resources identified to develop this plan: however, actions to increase the availability of temporary accommodation already being developed and delivered: 3 more homes leased from EMH, 12 new leased homes at a late stage of negotiation with a private-sector provider, 1 new lease from Futures planned for December, 92 EMH homes redesignated from older people to people younger than 60 to help move-on from temporary accommodation and negotiations underway to use a local hotel in the borough for some B&B.
| Improve quality of life | 2.3a | Actively support delivery of the Erewash Health & Wellbeing Partnership Plan to respond to the needs of targeted groups | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Erewash H&W Partnership Priorities reviewed and agreed with executive group. Ongoing delivery and development of Community Wellness Approach.
| Improve quality of life | 2.3b | Deliver key Shared Prosperity Fund (SPF) projects including the new 3G pitch at Rutland Sports Park and the destination play facility at West Park | Resources | Planning | Steve Birkinshaw | Green | West Park Play facility - 1 of 2 playgrounds complete; work underway on second. 3G pitch - work commenced, due to be completed by the end of October.
| Improve quality of life | 2.3c | Work with partners to support delivery of the Erewash Community Safety Partnership Plan to respond to crime, anti-social behaviour and the fear of these | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Plan approved at the Strategic Group meeting on 15.10.24 with priorities of Neighbourhood Crime and Anti-Social Behaviour, and Violence, Organised Crime and Exploitation. Delivery Plans developed to sit behind the Plan to show activity and action to deliver against the priorities.
| Improve quality of life | 2.3d | Actively support the Voluntary and Community Sector through encouraging volunteering and, where possible, financial or other support | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Ongoing collaboration and conversation with the VCS, including through Erewash Voluntary Action. Fast Funding Grants to voluntary groups / organisations through UK SPF has seen 14 projects receiving a share of £17,240 awarded during Q1/Q2 of 2024/25.
| Improve quality of life | 2.3e | Deliver a varied and exciting programme of events, cultural activities and museum services, alongside securing reaccreditation of Erewash Museum from Arts Council England | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Cultural Events Programme exceeding targets year to date. Varied programme of events during summer period. Exhibitions agreed for remainder of 2024. Work underway to achieve Arts Council England reaccreditation in 2025.
| Improve quality of life | 2.3f | Delivery of £24.8m Long Eaton Town Deal programme, including West Park lighting scheme, Broad Street Bridge and waterside improvements | Resources | Planning | Tom Haddock | Green | West Park Lighting Project substantially complete. Britania Mills Bridge, Broad Street Bridge and Waterfront have obtained planning consent and are now in the detailed design stage with early contractor involvement. Galaxy Row - Procurement of Development Partner ongoing.

## Priority 3
Sustainable Environment Actions
Reporting period
Q2 2024-25
Summary All actions have commenced and are progressing to target.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 10 | 100%
Summary |  |  |  |  | Completed | 0 | 0%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update
| Deliver and respond to climate change | 3.1a | Publish an Annual Climate Change Statement as well as engage and raise awareness of actions residents and partners can take in response to climate change | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | The council's first annual climate change statement for 2022-23 was approved by the Council Executive on 24 February 2024. The annual statement for 2023-24 is now being prepared.
Financial Summary | Deliver and respond to climate change | 3.1b | Establish and publish a new corporate Climate Change Strategy and action plan | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Key headline content for the strategy was agreed by the Climate Change Action Working Group on 11/9/2024.
| Deliver and respond to climate change | 3.1c | Pursue opportunities for investment (when available/externally secured) to support decarbonisation of the council’s operations, property and fleet assets | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Fleet review underway, including consideration of alternative fuel use. Ongoing schemes for decarbonisation works at the leisure centres following successfully securing £2.8m of external grant funding. Property and Estates to liaise with the Climate Change Officer regarding further schemes and external grant opportunities.
Risks | Deliver and respond to climate change | 3.1d | Facilitate the promotion and retrofitting of energy efficiency measures and low carbon technologies in eligible residential properties | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Dedicated officer in place (fixed-term) to lead programmes with Home Upgrade Grant Phase 2 (HUG2), UK Shared Prosperity Funding (UKSPF) and Devolution funding projects all being delivered. 32 households have benefitted to date with a further 8 anticipated to benefit by year end. Solar panels and wall insulation are the most common measures. Service about to express an interest in the new national funding for energy efficiency measures, Warm Homes: Local Grant (WH:LG) from April 2025.
| Implement new waste management | 3.2a | Implement new statutory food waste household collections and promote participation | Environmental & Community Services | Operational Services | Dave Bramwell | Green | The deadline is April 2026 for household food waste collections with confirmation awaited on national revenue funding. Appropriate refuse collection vehicles ordered and awaiting delivery utilising the national capital funding allocation. Work continues to develop the plans to implement the new service. Consideration is also being given to the implications for the commercial waste collection service which is subject to different deadlines.
| Implement new waste management | 3.2b | Encourage residents to produce less waste and recycle more | Environmental & Community Services | Operational Services | Dave Bramwell | Green | New recycling contract in place. Feedback from provider monitored, with regular meetings, which will assist the council to deliver targeted campaigns via social media and press releases, where required.
| Look after the borough’s green spaces | 3.2c | Implement rewilding of the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Previous rewilding plan implemented successfully. Following engagement and feedback, some in-year changes and amendments to schedules have been made. Discussions in place with members to finalise future modifications to the scheme and to build on the community engagement (eg links with young people/schools/friends of groups).
| Look after the borough’s green spaces | 3.3a | Establish the new Pewit Coronation Meadows local nature reserve | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Work on site has commenced. So far we have installed 3 footpaths, 3 butterfly banks, litter bins and seating. Ongoing works to achieve local nature reserve status.
| Look after the borough’s green spaces | 3.3b | Maintain the high standards of West Park and Victoria Park for community use | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Ongoing maintenance schedules at both sites as agreed with members, with a view to continuing the provision of high quality green spaces.
| Look after the borough’s green spaces | 3.3c | Continue the provision of sports pitches and play parks across the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Junior football pitch added at West Park. Maintenance of all other relevant sites continues.

## Priority 4
A Modern Council Actions
Reporting period
Q2 2024-25
Summary All commenced actions are on target, with five already completed. Just one action not started yet, the Invest to Save policy. This is still expected to be completed within the first 2 years of the Corporate Strategy action plan.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 7 | 58.33%
Summary |  |  |  |  | Completed | 5 | 41.67%
Delivery Plan |  |  |  |  | Not started | 1
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update
| Make best use of resources | 4.1a | Review of the Council Constitution to enable more efficient ways of working | Resources | Law & Governance | Danielle Hughes | Green | The Financial Regulations have been reviewed and are due to be considered by Full Council on 31/10/2024. The Contract Procedure Rules are also being reviewed and will come to Full Council in due course.
Financial Summary | Make best use of resources | 4.1b | Introduce a new workforce development strategy aimed at developing a suitably skilled, motivated and engaged workforce | Resources | Human Resources | Jo Watts | Completed | This was presented to and approved by the Executive in October. The council is investing £80,000 into staff training and recruiting a Learning and Development officer to support improvements in front line departments.
| Make best use of resources | 4.1c | Enhance Member and staff training and development programme | Resources | Law & Governance | Danielle Hughes/Jo Watts | Green | A member survey is currently in circulation (closing date October 24). This will help inform the draft Member Development Programme. The new E-Learning platform will be live in the new year for staff and Members.
Risks | Make best use of resources | 4.1d | Develop and implement new Property Asset Management Plan including the disposal of surplus council assets | Environmental & Community Services | Property & Estates | Tom Haddock | Completed | Property Asset Management Plan approved by the Council Executive on 01 October 2024, subject to call in. The council is continuing with its asset disposal plan and with improvements to current assets such as leisure centres using government grants.
| Make best use of resources | 4.1e | Develop a modern approach to communication with an emphasis on refreshing the approach to consultation and engagement and consultation | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | A new monthly e-newsletter for residents was launched in September, backed by a successful marketing communications programme – subscription levels of 5k plus have been achieved over a short period and an open rate of 74% registered for the October newsletter, well above the average of 40% for other public sector organisations. A staff e-newsletter is also being developed with expected launch in November. Staff training is already underway on the new public consultation and engagement platform, Engagement HQ which is expected to be launched in December – this will help improve engagement, consultation, and resident participation
| Ensure financial stability | 4.2a | Deliver planned savings in 2024/25 and a balanced budget in 2025/26 | Resources | Accountancy | Judy Fay | Green | Budget development in progress. Monitoring of savings achieved is reported quarterly to Council Executive.
| Ensure financial stability | 4.2b | Develop a ten-year capital programme setting out long term investment and maintenance plans | Resources | Accountancy | Judy Fay | Green | The long term capital programme is in progress. Further work is required.
| Ensure financial stability | 4.2c | Develop Invest to Save Policy to provide a framework for investment | Resources | Accountancy | Judy Fay | Not started | Due to start in 2025/26. For now, any invest to save initiatives will be considered on a case by case basis.
| Ensure financial stability | 4.2d | Develop Productivity Plan as required by Government | Resources | Accountancy | Judy Fay | Completed | Productivity Plan reported to Council Executive July 2024. We have had no feedback from Government other than a letter confirming that the "asks" made of Government will be considered.
| Ensure financial stability | 4.2e | Respond to Government funding consultation and lobby for additional funding for Erewash | Resources | Accountancy | Judy Fay | Green | Spending Review submission completed by the Director of Resources based on the Productivity Plan produced and agreed by Members.
| Utilise technology to transform service delivery | 4.3a | Develop an ICT and digital strategy (including assessment of investment required) to enable more efficient working and protect the council from cyber risk | Resources | ICT | Andy Nix | Completed | ICT Strategy presented to and approved by Council Executive on 1st October 2024. The council is investing over £300,000 in various projects including a new website, improvements in the Erewash Account and a new Planning and Building Control system that will be better for customers.
| Utilise technology to transform service delivery | 4.3b | Implement new waste management system | Environmental & Community Services | ICT | Andy Nix | Completed | System implemented successfully. The system has been used to implement Garden Waste subscriptions and improve operational efficiency in the way missed bins are dealt with.
| Utilise technology to transform service delivery | 4.3c | Review customer portal and options for increasing ability to transact online to support channel shift | Resources | ICT | Andy Nix | Green | This is in progress. We have identified areas where there are options for increasing ability to do things online e.g. complaints, Freedom of Information requests, road closures. Changes to the Customer Portal will happen after the new website has been implemented.

## Performance Indicators
Key Performance Indicator library
Reporting period
Q2 2024-25 | To support the new Corporate Strategy, and in addition to the Delivery Plan, we have introduced a new suite of Key Performance Indicators (KPIs). As with the Deliver Plan Actions, these are split by Corporate Priority: 1. Economy and Regeneration 2. Supporting Communities 3. Sustainable Environment 4. A Modern Council Performance is reported quarterly, with the exception of indicators that those that are measured at year-end. For those with an outturn, a 'Red, Amber, Green' rating, to show whether the indicator has met target. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary
Risks

## KPI 1
Economy and Regeneration Indicators
Reporting period
Q2 2024-25
Summary Only 1 indicator is short of target, marginally, with one major planning application exceeding the timescale for processing,
Home | [5 empty] | Red | 0 | 0%
[6 empty] | Amber | 1 | 16.67%
Summary | [5 empty] | Green | 5 | 83.33%
Delivery Plan | [5 empty] | Not started/annual | 1
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 2 position | RAG | Commentary
| ER - 1 | -1 | Processing of major planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 90.3% | Quarterly | 87.5% | Amber | There have been 7 major applications processed in the year to date but 1, in September, exceeded the timescale
Risks | ER - 2 | -2 | Processing of minor planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 96.8% | Green | There have been 63 minor applications processed in the first half of this year.
| ER - 3 | -3 | Processing of other planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 99.1% | Green | There have been 213 'other' applications processed in the first half of this year.
| ER - 4 | -4 | Percentage of major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 4% | Quarterly | 0% | Green | No decisions on major applications this year
| ER - 5 | -5 | Percentage of non-major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 1% | Quarterly | 0.36% | Green | 279 minor/other applications in the year to date, with 1 overturned on appeal.
| ER - 6 | -6 | Number of new homes completed | Resources | Planning Policy | Steve Birkinshaw |  | Year-end | - | - | -
| ER - 7 | -7 | Number of businesses supported by Erewash Partnership | Resources | Planning Policy | Steve Birkinshaw | 50 | Year-end | 50 | Green | Established businesses receive non-financial assistance and support from the partnership, under a Service Level Agreement with the council.

## KPI 2
Supporting Communities Indicators
Reporting period
Q2 2024-25
Summary Just one red indicator, for homelessness prevention.
Home | [5 empty] | Red | 1 | 7.692%
[6 empty] | Amber | 2 | 15.38%
Summary | [5 empty] | Green | 10 | 76.92%
Delivery Plan | [5 empty] | For info only | 1
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 2 position | RAG | Commentary
| SC - 1 | -1 | The percentage of dangerous structures reported to the building control service that were responded to within 24 hours | Environmental & Community Services | Building Control | Nick Thurstan | 95% | Quarterly | 100% | Green | During the monitoring period, 31 dangerous structures were reported. Manual interrogation of these records has confirmed that in all cases action was taken promptly to investigate and resolve the issues raised. However, a first response time was not recorded in 15 of the cases investigated to enable a meaningful comparison to be made against the indicator. For the 16 that did have a first resonse record, these were all within 24 hours. Reporting arrangements have been updated to ensure that for Q3 and 4, first response times will be recorded in all cases.
Risks | SC - 2 | -2 | Number of residents participating in council-run or partnered health and wellbeing programmes | Environmental & Community Services | Communications & Culture | Stewart Millar | 1400 | Quarterly | 1828 | Green | Outturn is measured cumulatively, with a profiled target throughout the year. Service delivered, Holiday Activity & Food schemes, summer activity programme, community wellness projects, walking and cycling schemes and community sport youth work.
| SC - 3 | -3 | Number of visitors to Erewash Museum | Environmental & Community Services | Communications & Culture | Stewart Millar | 10000 | Quarterly | 10340 | Green | Outturn is measured cumulatively, with a profiled target throughout the year. Service delivered a number of new exhibitions and events alongside SPF events programme. Installation of new cafe in Q1 resulted in an increase of regular visitors.
| SC - 4 | -4 | Customer complaints responded to within timescales | Environmental & Community Services | Communications & Culture | Stewart Millar | 95% | Quarterly | 94% | Amber | 3 out of 50 took longer than the current 20 day target
| SC - 5 | -5 | Number of organisations supported by Fast Fund Community Grants | Environmental & Community Services | Communications & Culture | Stewart Millar | TBC | Quarterly | 14 | For info | Fast Funding Grants to voluntary groups / organisations through UK Shared Prosperity Fund has seen 14 projects receiving a share of £17,240 awarded during Q1/Q2 of 2024/25.
| SC - 6 | -6 | Percentage of food safety inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 90% | Quarterly | 90% | Green | So far this year Environmental Health have inspected 182 premises for food safety.
| SC - 7 | -7 | Percentage of animal welfare premises inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 90% | Quarterly | 100% | Green | Environmental health have inspected 13 animal welfare premises this year.
| SC - 8 | -8 | Percentage of homelessness prevention cases received during the financial year closed with a successful outcome. | Environmental & Community Services | Homelessness | Nick Thurstan | 50% | Quarterly | 43% | Red | Lack of available accommodation is making prevention harder to attain. The Council owes a duty to prevent homelessness for people at risk of homelessness, for a period of 56 days. At the end of the 56 day period, if the applicant continues to be at risk of homelessness or has become homeless then the Council's duty alters to a relief duty. The relief duty lasts a further 56 days. At the end of the relief duty should the applicant remain homeless, the Council must decide what main duty is owed to the individual. For those who have a priority need (defined in legislation) who are homeless through no fault of their own, this will be a duty to provide accommodation. For those who do not have a priority need or who are found to be intentionally homeless the Council's duty will be to provide advice and assistance but not accommodation. Those assessed as being intentionally homeless are referred to social care to see if a duty is owed under the Care Act 2014. The target is based on national performance outcomes for England 2023/24
| SC - 9 | -9 | Percentage of homelessness relief cases received during the financial year closed with a successful outcome | Environmental & Community Services | Homelessness | Nick Thurstan | 30% | Quarterly | 73% | Green | The target is based on national performance outcomes for England 2023/24
| SC - 10 | -10 | Percentage of licensed premises compliant with licensing requirements within 21 days following initial intervention by the council | Environmental & Community Services | Licensing | Nick Thurstan | 90% | Quarterly | 100% | Green | 42 licensed premises visited this year. 3 were found to be non-compliant, initially, but all were then compliant within 21 days of intervention.
| SC - 11 | -11 | Percentage of licence applications under the Licensing Act determined within 5 working days (following consultation except where the application is referred to a Licensing and Public Protection Panel) | Environmental & Community Services | Licensing | Nick Thurstan | 90% | Quarterly | 100% | Green | 73 applications were determined in the first 2 quarters of the year, all within 5 working days.
| SC - 12 | -12 | Percentage of homes made safe to live in where a serious hazard has been identified on inspection | Environmental & Community Services | Private sector housing | Nick Thurstan | 90% | Quarterly | 100% | Green | 6 Category 1 hazards identified within 6 private rented properties, removed/reduced following our intervention within the specified timescales.
| SC - 13 | -13 | Revs and bens - time (days) taken to process new Housing Benefit claims | Resources | Revenues & Benefits | Lisa Black | 19 | Quarterly | 17.9 | Green | Outturn is measured cumulatively. There were 327 new Housing Benefit claims in the first half of the year.
| SC - 14 | -14 | Revs and Bens Time (days) taken to process Housing Benefit change of circumstances | Resources | Revenues & Benefits | Lisa Black | 9 | Quarterly | 9.6 | Amber | Outturn is measured cumulatively. There were 3,042 change of circumstances processed in the first half of the year.

## KPI 3
Sustainable Environment Indicators
Reporting period
Q2 2024-25
Summary Two amber indicators, both for Waste and Recycling. These are always reported one quarter in arrears as the data is not available until submitted to government, usually after the reporting period for the relevant quarter.
Home | [5 empty] | Red | 0 | 0%
[6 empty] | Amber | 2 | 50%
Summary | [5 empty] | Green | 2 | 50%
Delivery Plan | [5 empty] | Not started/annual | 3
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 2 position | RAG | Commentary
| SE - 1 | -1 | Percentage of permits for polluting industrial processes due during the year completed | Environmental & Community Services | Environmental Protection | Nick Thurstan |  | Quarterly | - | - | No permit inspections were due in the first 2 quarters. 3 are due in quarter 3 and 18 in quarter 4
Risks | SE - 2 | -2 | Percentage of Environmental Protection first responses to service requests completed within 3 working days | Environmental & Community Services | Environmental Protection | Nick Thurstan | 90% | Quarterly | 98.5% | Green | Environmental Protection have responded to 515 service requests.
| SE - 3 | -3 | Residual waste per household (kg) | Environmental & Community Services | Waste and Recycling | Dave Bramwell | Not more than 121.5 | Quarterly | 133.62 | Amber | Outturn is for Quarter 1 2024-25, reported 1 quarter in arrears
| SE - 4 | -4 | Household waste recycling/composting rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell | 42% | Quarterly | 41% | Amber | Outturn is for Quarter 1 2024-25, reported 1 quarter in arrears
| SE - 5 | -5 | Recycling contamination rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell |  | Quarterly |  | - | There is no target for this indicator at present. We have just moved to a new contractor for waste services. We will use the first year’s total as a benchmark for future performance.
| SE - 6 | -6 | Number of missed bins per 100k collections | Environmental & Community Services | Waste and Recycling | Dave Bramwell | Not more than 105 | Quarterly | 100.9 | Green | 1,321 missed bins in the first 2 quarters, out of over 1.3 million collections (0.1%).
| SE - 7 | -7 | Reduction in the council's CO2 emissions | Environmental & Community Services | Environmental Protection | Nick Thurstan |  | Year-end | - | - | -

## KPI 4
A Modern Council Indicators
Reporting period
Q2 2024-25
Summary One red indicator and two amber. For the post vacancy rate, this is not entirely within out control. Council Tax collection is short of the profiled target for the end of Quarter 2, but we are confident the year-end target will be met.
Home | [5 empty] | Red | 1 | 7.143%
[6 empty] | Amber | 2 | 14.29%
Summary | [5 empty] | Green | 11 | 78.57%
Delivery Plan | [5 empty] | Not started/annual | 1
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 2 position | RAG | Commentary
| AMC - 1 | -1 | Post vacancy rate | Resources | Human Resources | Jo Watts | Not more than 12% | Quarterly | 17% | Red | In common with other councils, recruitment and retention continues to be a challenge. There is no one specific cause and the council is trying a number of different approaches to address this issue.
Risks | AMC - 2 | -2 | Number of data breaches referred to ICO | Resources | Law & Governance | Danielle Hughes | 0 | Quarterly | 0 | Green | There have been 5 confirmed personal data breaches reported in the year to date, up from 4 in the first 2 quarters in 2023/24. None were considered enough of a risk to report to the ICO
| AMC - 3 | -3 | Percentage of FOI and EIR requests processed within 20 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 98.1% | Green | 670 requests received in the year to date (337 FOI, 333 EIR). This is similar to the same point last year (672)
| AMC -4 | -4 | Percentage of Subject Access Requests processed within 1 month | Resources | Law & Governance | Danielle Hughes | 90% | Quarterly | 92.3% | Green | 13 SARs processed in the year to date; 1 took over 2 months due to the complexity of the case
| AMC - 5 | -5 | Percentage of agendas published 5 working days before meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | 25 agendas have been published in the year to date.
| AMC - 6 | -6 | Percentage of minutes published 10 working days following meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 90.91% | Amber | 22 sets of minutes have been published in the first 2 quarters. July Scrutiny (waiting for information from Members) and August Council (significant pressure on resources in the Democratic Services team) took over 10 days to publish.
| AMC - 7 | -7 | Land charges requests processed within 10 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | There have been 1,123 Land Charges requests processed in the year to date. The average response time is 7 working days
| AMC - 8 | -8 | Business Rates Collection rates (NNDR) - in year | Resources | Revenues & Benefits | Lisa Black | 58% | Quarterly | 58.74% | Green | Outturn is measured cumulatively, with a profiled target throughout the year. Performance is on target for year-end outturn; 58.74% represents £11.5m collected
| AMC - 9 | -9 | Council Tax Collection rates - in year | Resources | Revenues & Benefits | Lisa Black | 59.5% | Quarterly | 58.25% | Amber | Outturn is measured cumulatively, with a profiled target throughout the year. Performance is slightly short of profile but is still on target for year-end outturn; 58.25% represents £43.55m collected
| AMC - 10 | -10 | Building Control service to achieve 3 year rolling break even | Environmental & Community Services | Building Control | Nick Thurstan |  | Year-end | - | - | -
| AMC - 11 | -11 | Average phone call wait time for the Contact Centre (minutes) | Environmental & Community Services | Communications & Culture | Stewart Millar | Not more than 6 | Quarterly | 3.5 | Green | Average response time of 3 minutes 50 seconds
| AMC - 12 | -12 | Balanced budget for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green
| AMC - 13 | -13 | Reserves projected to be of minimum for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | Based on the current MTFP this is forecast to be achieved
| AMC - 14 | -14 | Statement of accounts published by May statutory deadline | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | 2023/24 Statement of Accounts published by 31 May deadline
| AMC - 15 | -15 | Percentage of invoices paid on time | Resources | Accountancy | Lisa Black | 95% | Quarterly | 96.47% | Green | There have been 7,113 invoices paid in the year to date, with 6,862 paid on time.

## Financial
Reporting period | Financial Summary
Q2 2024-25 | The Council's performance against its budget is reported quarterly to the Council Executive and to Scrutiny. More information about how we are doing can be found there. We have listed below, for information, a range of financial indicators produced by the Office for Local Government – some of which are outside the control of the Council
Home
Summary
|  | Indicator ref | Indicator | Directorate | Service | Owner | Target | Quarter 2 position | RAG | Comments
Delivery Programme |  | FS1 | Total core spending power per dwelling | Resources | Accountancy | Judy Fay | For info | 238 | For info | The core spending power is extracted from the local government financial settlement. CSP for 2023-24 was £225, increasing to £238.
|  | FS2 | Total debt as percentage of core spending power | Resources | Accountancy | Judy Fay |  | 0% | Green | Council has zero long term borrowing
Performance Indicators |  | FS3 | Non-ringfenced reserves as percentage of net revenue expenditure | Resources | Accountancy | Judy Fay |  | Annual | Annual | Outturn will be provided once year-end expenditure is confirmed.
|  | FS4 | Council tax revenue per dwelling | Resources | Revenues & Benefits | Lisa Black | For info | 141.31 | For info | Figure based on the local government finance settlement
Financial Summary |  | FS5 | Level of band D council tax rates | Resources | Revenues & Benefits | Lisa Black | For info | 213.83 | For info | This is the council tax for Erewash only, excludes police, fire etc.
|  | FS6 | Debt servicing as percentage of core spending power | Resources | Accountancy | Judy Fay |  | 0% | Green | Council has zero long term borrowing
Risks |  | FS7 | Balanced budget for current year | Resources | Accountancy | Judy Fay | For info | Yes | For info
|  | FS8 | Gross external debt | Resources | Accountancy | Judy Fay |  | 0% | Green | Council has zero long term borrowing
|  | FS9 | Auditor approved accounts | Resources | Accountancy | Judy Fay | For info | No | For info | 2021/22 accounts approved, 2022/23 to be disclaimed, 23/24 accounts to be audited by February 2025.

## Risks
Risks
Reporting period
There has been a little movement in the Strategic Risk Register this quarter (reported September 2024). Risk 1 (Key priority delivery) and Risk 5 (ICT infrastructure) have both reduced in likelihood of occurence. There is a new risk added, Risk 9 - Cyber attack against the Council preventing delivery of critical services and/or breach or corruption of data. This was previously included in Risk 7 (GDPR compliance), but has been moved to its own risk, to reflect the potential impact, were we to suffer such an attack. For more information, please see the September 2024 Audit Committee Strategic Risk Register item at the link below.
Q2 2024-25
Home
Summary
Delivery Plan
Performance Indicators
Financial Summary |  |  |  | https://moderngov.erewash.gov.uk/ieListDocuments.aspx?CId=285&MId=2384&Ver=4
Risks |  | Risk | Description | Date added | Inherent risk score | Residual risk score | Latest movement | Latest update
|  | Risk ID 1 – Key priorities delivery | There is a risk we cannot deliver key/new priorities due to a lack of resources caused by retention/recruitment issues, budget or too big a corporate workload (including additional requirements from Government). | 2023-05-01 | 20 | 12 | é | Risk score reduced from 16 (4x4) to 12 (4x3) reflective of reduction in likelihood ('Even chance') given current budget management and new Corporate Plan.
|  | Risk ID 2 – Financial stability | There is a risk that the Council is not financially stable in the medium term (as evidenced by the gap in MTFF) due to uncertain future government funding. | 2019-06-01 | 25 | 20 | çè | No risk change – updates to controls and comment section reflecting 23/24 outturn and 24/25 quarter 1 position.
|  | Risk ID 3 – Housing land supply | Failure to demonstrate adequate housing land supply resulting in various impacts - a shortfall each year in property available for sale, house price inflation, local residents leaving the Borough or new people not moving in and loss of council tax base of £225,000 per year. | 2016-07-01 | 15 | 12 | çè | No risk change – updates to controls and comment section to reflect latest position regarding announcement of consultation on reforms to the National Policy Planning Framework (NPPF).
|  | Risk ID 4 – Long Eaton Town Board | The Town Board not able to deliver on one or more of its key projects resulting in failure to meet objectives, financial loss, reputational damage and frustration for residents. Risk includes construction cost inflation, council capacity to develop multiple projects, contractor administration risk, delays in design agreements, funding restricted to committed costs and completion deadline. | 2022-03-01 | 16 | 9 | çè | Risk wording enhanced. New actions added to reflect monitoring of cost inflation.
|  | Risk ID 5 – ICT infrastructure | Lack of appropriate ICT/digital infrastructure undermines Council’s ability to deliver on its priorities and/or creates inefficiencies. | 2023-03-01 | 16 | 6 | é | Reduction in risk score from 9 (3x3) to 6 (3x2) reflecting a reduction in likelihood ('Unlikely') now Head of IT in post and progress being made on a number of actions and gaps better understood.
|  | Risk ID 6 – Business Continuity | Failure to deliver key services should a significant business interruption occur. | 2023-05-01 | 16 | 9 | çè | No change to risk. Wording updates to actions and controls, particularly around progress made by service areas updating their BCP’s.
|  | Risk ID 7 – GDPR compliance | Information Governance / GDPR Risk: There is a risk that the Council suffers a data protection breach arising from poor processes and controls, accidental or intentional actions including cyber attack, leading to potential harm to individuals, employees and members, legal action, financial penalties from ICO and reputational damage. | 2023-12-01 | 20 | 6 | çè | Risk description altered – Cyber risk previously included in this risk, but has now been moved to a separate risk on its own (see risk 9) A number of actions completed.
|  | Risk ID 8 – Temporary Accommodation | There is a risk of significant overspend on supported housing and temporary accommodation, in order for the Council to deliver its duty on homelessness under the Housing Act 1996 and manage its duty around accommodation of families with children/pregnant women. | 2023-12-01 | 25 | 20 | çè | No overall change to risk. Actions updated. Minor wording updates to controls.
|  | Risk ID 9 – Cyber Attack | Cyber attack against the Council preventing delivery of critical services and/or breach or corruption of data. | 2024-09-01 | 12 | 12 | New | New risk added to register (previously included in risk 7) Risk score 12 (4x3). Actions and controls documented.

## Lookup (hidden)
Q2 2024-25 | 2024-09-30 | Q2 2024-25
Q3 2024-25 | 2024-12-31 | Q3 2024-25
Q4 2024-25 | 2025-03-31 | Q4 2024-25
Q1 2025-26 | 2025-06-30 | Q1 2025-26
Q2 2025-26 | 2025-09-30 | Q2 2025-26
Q3 2025-26 | 2025-12-31 | Q3 2025-26
Q4 2025-26 | 2026-03-31 | Q4 2025-26
Q1 2026-27 | 2026-06-30 | Q1 2026-27
Q2 2026-27 | 2026-09-30 | Q2 2026-27
Q3 2026-27 | 2026-12-31 | Q3 2026-27
Q4 2026-27 | 2027-03-31 | Q4 2026-27
Q1 2027-28 | 2027-06-30 | Q1 2027-28
Q2 2027-28 | 2027-09-30 | Q2 2027-28
Q3 2027-28 | 2027-12-31 | Q3 2027-28
Q4 2027-28 | 2028-03-31 | Q4 2027-28
Q1 2028-29 | 2028-06-30 | Q1 2028-29
Q2 2028-29 | 2028-09-30 | Q2 2028-29
Q3 2028-29 | 2028-12-31 | Q3 2028-29
Q4 2028-29 | 2029-03-31 | Q4 2028-29
Q1 2029-30 | 2029-06-30 | Q1 2029-30
Q2 2029-30 | 2029-09-30 | Q2 2029-30
Q3 2029-30 | 2029-12-31 | Q3 2029-30
Q4 2029-30 | 2030-03-31 | Q4 2029-30
Q1 2030-31 | 2030-06-30 | Q1 2030-31
Q2 2030-31 | 2030-09-30 | Q2 2030-31
Q3 2030-31 | 2030-12-31 | Q3 2030-31
Q4 2030-31 | 2031-03-31 | Q4 2030-31
Q1 2031-32 | 2031-06-30 | Q1 2031-32
Q2 2031-32 | 2031-09-30 | Q2 2031-32
Q3 2031-32 | 2031-12-31 | Q3 2031-32
Q4 2031-32 | 2032-03-31 | Q4 2031-32
Q1 2032-33 | 2032-06-30 | Q1 2032-33
Q2 2032-33 | 2032-09-30 | Q2 2032-33
Q3 2032-33 | 2032-12-31 | Q3 2032-33
Q4 2032-33 | 2033-03-31 | Q4 2032-33
Q1 2033-34 | 2033-06-30 | Q1 2033-34
Q2 2033-34 | 2033-09-30 | Q2 2033-34
Q3 2033-34 | 2033-12-31 | Q3 2033-34
Q4 2033-34 | 2034-03-31 | Q4 2033-34